## Worksheet
Task | Assigned To | Due Date | Priority | Status | Estimated Hours | Actual Hours
Project Planning Meeting | Team Lead | 2024-04-15 | High | Completed | 4 | 4
Design Phase Finalization | Designer A | 2024-04-20 | High | In Progress | 10 | 6
Development Setup | Developer B | 2024-04-18 | Medium | Not Started | 5 | 0
QA Testing Plan Review | QA Manager | 2024-04-25 | Medium | Scheduled | 8 | 0
Team Retrospective Session | Team Lead | 2024-04-30 | Low | Not Started | 3 | 0