## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Duration (Days) | Dependencies | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | High | Completed | 1 |  | Initial project alignment and goals setting.
T002 | Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | High | In Progress | 14 | T001 | Collect input from stakeholders and document functional requirements.
T003 | Design Phase | Lisa Chen | 2024-04-16 | 2024-05-10 | Medium | Not Started | 35 | T002 | Create UI/UX prototypes and system architecture.
T004 | Development Phase | Mike Brown | 2024-05-11 | 2024-07-30 | High | Not Started | 90 | T003 | Build core modules and integrate with APIs.
T005 | Testing & QA | Sarah Lee | 2024-08-01 | 2024-08-31 | High | Not Started | 60 | T004 | Conduct unit, integration, and user acceptance testing.