## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-01 | High | Completed | All team members present, objectives agreed.
T002 | Market Research Analysis | David Chen | 2024-04-03 | 2024-04-10 | Medium | In Progress | Data collection phase ongoing.
T003 | Development Phase Planning | Lisa Patel | 2024-04-11 | 2024-04-25 | High | Not Started | Finalize technical roadmap and resource allocation.
T004 | Client Presentation Draft | Mark Wilson | 2024-04-15 | 2024-04-18 | High | Pending Review | Draft reviewed by design team for feedback.
T005 | Final Quality Assurance Testing | Elena Rodriguez | 2024-04-26 | 2024-04-30 | Medium | Not Started | Verify all features and bug fixes.