## Worksheet
Task ID | Task Name | Due Date | Priority | Assigned To | Status | Estimated Hours | Actual Hours
T001 | Project Kickoff Meeting | 2023-10-15 | High | John Smith | Completed | 4 | 4
T002 | <Market Research Analysis | 2023-11-03 | Medium | Sarah Lee | In Progress | 8 | 3.5
T003 | Design Phase Final Review | 2023-11-18 | High | Mike Chen | Pending | 6 | 0
T004 | Client Presentation Draft | 2023-12-05 | Medium | Emily Wong | Not Started | 5 | 0
T005 | Final Budget Approval | 2023-12-15 | High | David Kim | Pending | 2 | 0