## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Duration (days) | Progress (%) | Dependencies
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | Low | 0 | 100 | None
T002 | Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-03-25 | In Progress | Medium | 10 | 60 | T001
T003 | UI/UX Design Final Review | Mike Chen | 2024-03-26 | 2024-04-01 | Pending | High | 5 | 0 | T002
T004 | Backend Development Start | Lisa Wang | 2024-04-02 | 2024-04-15 | Planned | Medium | 14 | 0 | T003
T005 | Testing Phase Initiation | David Kim | 2024-04-16 | 2024-05-05 | Not Started | High | 20 | 0 | T004