## Worksheet
Task ID | Task Title | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Location | Notes
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | In Progress | None | Conference Room A
TSK-002 | Market Research Report | John Doe | 2024-04-05 | 2024-04-15 | Medium | Not Started | TSK-001 | Office – North Wing | Include competitor analysis.
TSK-003 | Product Design Finalization | Lisa Chen | 2024-04-18 | 2024-05-03 | High | Planned | TSK-002, TSK-004 | Design Studio B | Must align with UX guidelines.
TSK-004 | Development Sprint Planning | Mike Brown | 2024-05-05 | 2024-05-31 | Critical | Not Started | TSK-003 | Development Lab | Need access to API documentation.
TSK-005 | Client Presentation & Review | Sarah Kim | 2024-06-10 | 2024-06-15 | High | Scheduled | TSK-004, TSK-003 | Client Conference Room | Final product demo required.