## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Dependencies
T001 | Finalize Q3 Budget Proposal | John Smith | 2024-04-01 | 2024-04-15 | On Track | High | 8 | 6 | Approval from Finance Team
T002 | Launch Marketing Campaign | Sarah Lee | 2024-04-10 | 2024-05-31 | In Progress | High | 20 | 12 | Content approved by Creative Director
T003 | Upgrade Server Infrastructure | Michael Chen | 2024-05-01 | 2024-06-15 | Planned | Medium | 30 | 0 | IT Review Complete
T004 | Team Training Session on New Software | Lisa Wong | 2024-04-25 | 2024-04-30 | Completed | Low | 5 | 5 | N/A
T005 | Prepare Annual Performance Review Documents | David Kim | 2024-03-15 | 2024-04-30 | Delayed | High | 15 | 9 | HR Approval Pending