## Worksheet
Task | Assigned To | Start Date | End Date | Priority | Status | Notes
Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | High | Pending | Confirm agenda and attendees.
Market Research Phase | Sarah Lee | 2024-04-02 | 2024-04-10 | Medium | In Progress | Collect data from 5 key customer groups.
Design Workshop | Mike Johnson | 2024-04-11 | 2024-04-15 | High | Not Started | Finalize wireframes and UI mockups.
Development Phase | Team A | 2024-04-16 | 2024-05-15 | High | Not Started | Build frontend and backend features.
Testing & QA Review | Lisa Chen | 2024-05-16 | 2024-05-31 | Medium | Not Started | Conduct functional and security tests.
Final Presentation | John Smith | 2024-06-01 | 2024-06-01 | High | Not Started | Present final results to stakeholders.