## Worksheet
Task | Assigned To | Start Date | End Date | Duration (days) | Priority | Status | Notes
Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Review project scope and objectives.
Design Phase Planning | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | Medium | In Progress | Finalize wireframes and user flows.
Development Setup | Mike Johnson | 2024-04-11 | 2024-04-15 | 5 | High | Not Started | Configure development environment and tools.
Testing & QA Review | Sarah Lee | 2024-04-16 | 2024-04-25 | 10 | High | Not Started | Run unit and integration tests.
Project Review & Delivery | Team Lead | 2024-04-26 | 2024-04-30 | 5 | Critical | Not Started | Final review, sign-off, and deployment.