## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Progress (%) | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | Medium | 100% | Meeting held successfully with stakeholders.
T002 | Requirement Gathering | John Smith | 2024-04-02 | 2024-04-15 | In Progress | High | 60% | Finalizing user stories from client interviews.
T003 | Design Phase Review | Lisa Brown | 2024-04-16 | 2024-04-20 | Planned | Medium | 0% | Waiting for final approval of wireframes.
T004 | Development Start | Mike Wilson | 2024-04-21 | 2024-05-15 | Not Started | Low | 0% | Initial codebase setup pending.
T005 | Testing & QA | Sarah Lee | 2024-05-16 | 2024-05-31 | Pending Approval | High | 20% | Smoke testing completed; integration issues pending.