## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resource Required | Dependencies | Notes
TSK-001 | System Upgrade Deployment | Jane Smith | 2024-04-15 | 2024-04-25 | High | In Progress | Dev Team, Cloud Engineers | TSK-003, TSK-004 | Rollout must follow backup protocol.
TSK-002 | User Access Review | Michael Lee | 2024-04-18 | 2024-04-23 | Medium | Pending | Security Analysts, HR Support | TSK-005 | Review access rights for all departments.
TSK-003 | Data Migration to New Platform | Sarah Kim | 2024-04-20 | 2024-05-10 | High | Scheduled | DBA Team, ETL Engineers | TSK-001, TSK-006 | Backup data before migration.
TSK-004 | Performance Optimization | David Wong | 2024-04-27 | 2024-05-15 | Medium | Not Started | Performance Engineers, DevOps | TSK-003 | Focus on API response times.
TSK-005 | Compliance Audit Preparation | Lisa Chen | 2024-04-16 | 2024-04-30 | High | In Progress | Compliance Officer, Legal Team |  | Prepare documentation for ISO 27001.