## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Start Date | Estimated Duration (Days)
TSK-001 | Develop Login Module | John Smith | High | 2023-10-15 | In Progress | 2023-10-01 | 7
TSK-002 | Design Database Schema | Emma Davis | Medium | 2023-10-25 | Not Started |  | 10
TSK-003 | Conduct User Testing | Liam Chen | High | 2023-11-10 | Scheduled | 2023-10-30 | 5
TSK-004 | Prepare Project Documentation | Sophia Rodriguez | Low | 2023-11-30 | Not Started |  | 14