## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Estimated Duration (Days) | Resource Required | Dependencies | Notes
T001 | Develop User Authentication Module | John Doe | 2024-03-15 | 2024-04-10 | High | In Progress | 30 | Backend, Frontend, Security Team | None | Must integrate with existing API gateway.
T002 | Design Mobile App UI/UX | Sarah Lee | 2024-03-20 | 2024-04-15 | Medium | Planned | 25 | UX Design Team, Product Manager | T001 Completion | Focus on accessibility and responsive layout.
T003 | Set Up CI/CD Pipeline | Mike Chen | 2024-03-18 | 2024-04-05 | High | Not Started | 15 | DevOps Team, Cloud Engineers | T004 Completion | Must support automated testing and deployment.
T004 | Conduct Security Audit | Lisa Wong | 2024-03-25 | 2024-04-18 | Critical | Not Started | 35 | Security Analysts, Compliance Team | None | Must comply with GDPR and ISO 27001 standards.
T005 | Train End-User Support Team | David Kim | 2024-04-10 | 2024-04-25 | Low | Planned | 10 | Support Team, Training Manager | T002 Completion | Include hands-on sessions and FAQs.