## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority Level | Status | Start Date | Estimated Duration (days) | Dependencies | Notes
T001 | Design Product UI | Alex Johnson | 2024-04-15 | High | In Progress | 2024-04-01 | 15 | None | Final mockups to be approved by PM.
T002 | Develop Backend API | Sam Rivera | 2024-04-30 | High | Not Started | 2024-04-10 | 20 | T001 (UI Design) | Integrate with authentication module.
T003 | Test Mobile App | Mia Chen | 2024-05-10 | Medium | Scheduled | 2024-04-18 | 7 | T002 (API Development) | Coverage test for iOS and Android.
T004 | User Training Workshop | Jordan Lee | 2024-05-15 | Low | Not Started | 2024-05-01 | 3 | T003 (Testing Complete) | Schedule for all department teams.