## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Cost (USD) | Budget Allocation
TSK-001 | System Upgrade Deployment | John Smith | 2024-03-15 | 2024-04-15 | In Progress | High | 80 | 65 | 4,200.00 | 5,000.00
TSK-002 | Financial Audit Report | Sarah Lee | 2024-03-20 | 2024-04-10 | Completed | Medium | 40 | 38 | 2,500.00 | 3,000.00
TSK-003 | User Training Program | Mike Johnson | 2024-03-25 | 2024-05-15 | Planned | Low | 30 | 0 | 1,500.00 | 2,000.00
TSK-004 | Security Patch Implementation | Lisa Wong | 2024-04-01 | 2024-04-15 | In Progress | High | 60 | 45 | 3,600.00 | 4,500.00