## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Progress (%)
TSK-001 | Design Brand Identity | Sarah Lee | 2024-04-01 | 2024-04-15 | High | In Progress | 80 | 65%
TSK-002 | Develop Mobile App UI | James Kim | 2024-04-05 | 2024-05-10 | Medium | Not Started | 40 | 0%
TSK-003 | Write Marketing Campaign | Maria Garcia | 2024-04-10 | 2024-04-25 | High | Completed | 15 | 100%
TSK-004 | Set Up Project Management Tools | David Chen | 2024-04-18 | 2024-04-20 | Low | Completed | 5 | 100%
TSK-005 | Conduct User Testing | Lena Patel | 2024-05-01 | 2024-05-15 | High | Not Started | 30 | 0%