## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Department | Estimated Hours | Progress (%)
TSK-001 | Develop Project Timeline | Sarah Johnson | 05/01/2024 | 05/15/2024 | High | In Progress | Project Management | 40 | 65%
TSK-002 | Finalize Budget Forecast | Michael Chen | 05/08/2024 | 05/30/2024 | Medium | Not Started | Finance | 30 | 0%
TSK-003 | Conduct User Training Sessions | Lisa Rodriguez | 05/10/2024 | 05/31/2024 | High | Scheduled | Support | 8 | 0%
TSK-004 | Review Vendor Contracts | David Kim | 05/14/2024 | 05/28/2024 | Medium | In Progress | 15 | 40%
TSK-005 | Deploy New CRM System | Elena Perez | 05/18/2024 | 06/05/2024 | High | Not Started | IT | 50 | 0%