## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Estimated Hours
T-001 | Design UI Mockups | Anna Lee | 2024-04-15 | High | In Progress | 2024-04-01 | 16
T-002 | Develop Backend API | James Wong | <2024-04-25 | High | Not Started | 2024-04-10 | 30
T-003 | Conduct User Testing | Sophia Kim | 2024-05-10 | Medium | Planned | 2024-04-30 | 8
T-004 | Optimize Database Queries | Michael Tran | 2024-04-30 | Medium | In Progress | 2024-04-18 | 12
T-005 | Prepare Project Documentation | Lena Patel | 2024-05-05 | Low | Not Started | 2024-05-01 | 6