## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Resource Required | Dependencies
TSK-001 | Design Product Prototype | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | UI/UX Designer, Product Manager | None
TSK-002 | Develop Backend API | Michael Chen | 2024-04-16 | 2024-05-10 | Medium | Pending | Backend Developer, DevOps | TSK-001
TSK-003 | Conduct User Testing | Sarah Lee | 2024-05-11 | 2024-05-25 | High | Not Started | Test Lead, QA Engineer | TSK-002
TSK-004 | Deploy to Staging Environment | David Kim | 2024-05-26 | 2024-06-03 | Medium | Planned | DevOps Engineer | TSK-003