## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date th> | Priority Level | Status | Estimated Duration (hrs) | Actual Duration (hrs) | Progress (%) | Dependencies
T001 | Project Planning Phase | Alice Johnson | 2024-03-15 | 2024-03-25 | High | In Progress | 80 | 65 | 75% | None
T002 | User Requirements Gathering | Bob Smith | 2024-03-18 | 2024-04-05 | High | Pending | 90 | - | 0% | T001
T003 | UI/UX Design Finalization | Carol Lee | 2024-04-01 | 2024-04-15 | Medium | Scheduled | 75 | - | 0% | T002
T004 | Development Phase - Backend | David Park | 2024-04-16 | 2024-05-30 | High | Not Started | 150 | - | 0% | T003
T005 | Testing & Quality Assurance | Eva White | 2024-06-01 | 2024-06-30 | Medium | Planned | 120 | - | 0% | T004
Total Tasks: 5 ¦ High Priority Tasks: 3