## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Completion Rate
T001 | Project Planning Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | Completed | High | 8 | 7.5 | 93.8%
T002 | Market Research Analysis | John Smith | 2024-04-05 | 2024-04-15 | In Progress | Medium | 20 | 12 | 60.0%
T003 | UI/UX Design Review | Lisa Chen | 2024-04-10 | 2024-04-25 | Pending | High | 35 | 0 | 0.0%
T004 | Development Sprint 1 | Team A | 2024-04-18 | 2024-05-03 | Scheduled | High | 80 | 0 | 0.0%
T005 | Final QA Testing | Mike Taylor | 2024-05-10 | 2024-05-15 | Not Started | Medium | 15 | 0 | 0.0%