## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
T001 | Project Planning Meeting | Alice Johnson | 2024-04-01 | 2024-04-03 | Completed | Medium | 8 | 8 | 100%
T002 | Design Phase Review | Bob Smith | 2024-04-05 | 2024-04-10 | In Progress | High | 16 | 10 | 62.5%
T003 | Development Sprint 1 | Charlie Brown | 2024-04-11 | 2024-04-18 | Pending | High | 40 | 0 | 0%
T004 | User Testing Phase | Diana Prince | 2024-04-20 | 2024-05-01 | Planned | Medium | 24 | 0 | 0%