## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Estimated Hours | Actual Hours | Progress (%)
TSK-001 | Market Research Analysis | 2024-04-01 | 2024-04-15 | Sarah Chen | High | In Progress | 8 | 6 | 75%
TSK-002 | Product Roadmap Finalization | 2024-04-10 | 2024-04-30 | James Rodriguez | Critical | Pending | 12 | 0 | 0%
TSK-003 | Client Presentation Prep | 2024-04-18 | 2024-04-25 | Maria Lopez | Medium | Completed | 4 | 4 | 100%
TSK-004 | Internal Audit Review | 2024-05-01 | 2024-05-15 | David Kim | High | Not Started | 10 | 0 | 0%