## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority Level | Status | Resource Allocation | Dependencies | Progress % | Notes
T-001 | Project Planning Phase | Jane Smith | 2024-03-15 | 2024-03-25 | 10 | High | In Progress | Team A + Manager | None | 75% | Finalize scope and milestones.
T-002 | Design Finalization | Mike Johnson | 2024-03-26 | 2024-04-10 | 15 | High | Pending Start | Design Team | T-001 Completed | 0% | Wait for project plan approval.
T-003 | Development Phase | Sarah Lee | 2024-04-11 | 2024-05-15 | 35 | Medium | Not Started | Dev Team + QA Lead | T-002 Completed | 0% | Initial coding and API integration.
T-004 | Testing & QA | David Brown | 2024-05-16 | 2024-06-05 | 20 | High | Scheduled | QA Team + Dev Support | T-003 Completed | 0% | Regression and performance testing.
T-005 | Deployment & Rollout | Lisa Chen | 2024-06-06 | 2024-06-15 | 10 | Critical | Not Started | Operations Team | T-004 Completed | 0% | Deploy to production with monitoring.