## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
T001 | Project Planning Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | Completed | High | 8 | 8 | 100%
T002 | Design Phase Final Review | Mike Johnson | 2024-04-05 | 2024-04-10 | In Progress | Medium | 20 | 15 | 75%
T003 | Development Sprint | Sarah Lee | 2024-04-11 | 2024-04-18 | Not Started | High | 40 | 0 | 0%
T004 | User Testing & Feedback | David Brown | 2024-04-20 | 2024-05-03 | Scheduled | Medium | 30 | 0 | 0%