## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
T-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | Completed | High | 4 | 4 | 100%
T-002 | Design Phase Planning | Jane Smith | 2024-04-05 | 2024-04-15 | In Progress | Medium | 20 | 12 | 60%
T-003 | Develop Core Modules | Alex Chen | 2024-04-16 | 2024-05-10 | Pending | High | 60 | 0 | 0%
T-004 | User Testing & Feedback | Maria Garcia | 2024-05-11 | 2024-05-30 | Scheduled | Medium | 30 | 0 | 0%
T-005 | Final Review & Deployment | Team Lead | 2024-06-01 | 2024-06-15 | Not Started | High | 25 | 0 | 0%