## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
T101 | Project Planning Meeting | Jane Smith | 2024-03-15 | 2024-03-16 | Completed | High | 4 | 4 | 100%
T102 | Design Phase Review | Alex Johnson | 2024-03-18 | 2024-03-20 | In Progress | Medium | 8 | 5 | 62.5%
T103 | Development Sprint | Sam Lee | 2024-03-21 | 2024-03-31 | Pending | High | 40 | 0 | 0%
T104 | QA Testing Cycle | Taylor Brown | 2024-04-01 | 2024-04-15 | Scheduled | Medium | 30 | 0 | 0%