## Worksheet
Task | Assigned To | Start Date | End Date | Status | Priority | Estimated Effort (hrs) | Progress (%)
Product MVP Design | Alex Morgan | 2024-04-01 | 2024-04-15 | In Progress | High | 80 | 65%
User Onboarding Flow | Sam Lee | 2024-04-05 | 2024-04-20 | Planned | Medium | 45 | 0%
API Integration | Jordan Park | 2024-04-10 | 2024-04-30 | Scheduled | High | 120 | 0%
Market Analysis Report | Tina Chen | 2024-04-03 | 2024-04-18 | Completed | Medium | 60 | 100%
Team Onboarding Workshop | Raj Patel | 2024-04-08 | 2024-04-12 | Completed | Low | 30 | 100%