## Worksheet
Task ID | Task Name | Scheduled Date | Assigned To | Priority Level | Status | Estimated Duration (hrs) | Progress (%)
T-001 | Market Research & Analysis | 2024-04-15 | Sarah Johnson | High | In Progress | 20 | 65%
T-002 | Product Design Finalization | 2024-04-20 | Mike Chen | High | Not Started | 35 | 0%
T-003 | User Testing Phase | 2024-05-01 | Lisa Wong | Medium | Scheduled | 15 | 0%
T-004 | Marketing Campaign Draft | 2024-04-18 | David Kim | Low | Completed | 10 | 100%
T-005 | Budget Review & Approval | 2024-04-25 | Emma Rodriguez | High | Pending Review | 25 | 40%