## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Estimated Hours | Actual Hours
T-001 | Project Planning Workshop | Alex Morgan | 2023-10-03 | 2023-10-07 | In Progress | High | 65% | 8 | 6.5
T-002 | Market Analysis Report | Samira Patel | 2023-10-05 | 2023-10-12 | Not Started | Medium | 0% | 12 | 0
T-003 | UI/UX Design Final Review | Jordan Lee | 2023-10-10 | 2023-10-18 | On Hold | High | 40% | 16 | 8
T-004 | Backend Development Phase 2 | Rohan Singh | 2023-10-15 | 2023-11-01 | In Progress | High | 75% | 24 | 18
T-005 | Client Presentation Preparation | Taylor Kim | 2023-10-20 | 2023-10-25 | Not Started | Critical | 0% | 6 | 0