## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resources
T001 | Project Initiation | Jane Smith | 2024-03-01 | 2024-03-05 | 5 | High | Planned | None | Project Manager, Finance Lead
T002 | Requirements Gathering | Mike Johnson | 2024-03-06 | 2024-03-15 | 10 | High | In Progress | T001 | Business Analysts, Stakeholders
T003 | Design Phase | Sarah Lee | 2024-03-16 | 2024-03-25 | 10 | Medium | Planned | T002 | UX Designers, Developers
T004 | Development | David Kim | 2024-03-26 | 2024-04-15 | 21 | High | Not Started | T003 | Software Developers, QA Team
T005 | Testing & QA | Lisa Chen | 2024-04-16 | 2024-04-30 | 15 | High | Planned | T004 | QA Engineers, DevOps
T006 | Deployment | Robert Brown | 2024-05-01 | 2024-05-03 | 3 | MediumPlanned | T005 | DevOps, Operations Team