## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation
T-001 | Project Initiation & Planning | John Smith | 2024-01-01 | 2024-01-15 | 15 | High | Planned |  | Project Manager, Team Lead
T-002 | Market Research & Analysis | Sarah Lee | 2024-01-16 | 2024-02-15 | 30 | Medium | In Progress | T-001 | Research Analysts (2)
T-003 | Product Design & Prototyping | Michael Chen | 2024-02-16 | 2024-04-30 | 75 | High | Planned | T-002 | Design Team (5)
T-004 | Development & Coding | Lena Torres | 2024-05-01 | 2024-08-31 | 130 | High | Not Started | T-003 | Software Developers (8)
T-005 | Testing & Quality Assurance | David Kim | 2024-09-01 | 2024-10-31 | 60 | Medium | Planned | T-004 | QA Team (3)
T-006 | Launch & Deployment | Emma Wong | 2024-11-01 | 2024-11-30 | 30 | High | Not Started | T-005 | Operations Team (4)
T-007 | Post-Launch Review & Feedback | John Smith | 2024-12-01 | 2024-12-31 | 30 | Low | Planned |  | Project Manager, Customer Support
Annual Project Plan - Task Scheduling |  |  |  |  | Version 1.0 ¦ Project Plan Template