## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
T001 | Project Initiation | John Smith | 2024-03-01 | 2024-03-05 | 5 | Planned | High
T002 | Requirements Gathering | Sarah Lee | 2024-03-06 | 2024-03-15 | 10 | In Progress | High | T001
T003 | Design Phase | Michael Brown | 2024-03-16 | 2024-03-25 | 10 | Planned | Medium | T002
T004 | Development Phase | Lisa Wong | 2024-03-26 | 2024-04-15 | 20 | Not Started | High | T003
T005 | Testing Phase | David Clark | 2024-04-16 | 2024-04-30 | 15 | Planned | High | T004
T006 | Deployment & Handover | Emma Taylor | 2024-05-01 | 2024-05-05 | 5 | Planned | Medium | T005