## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | Completed | High | None | Initial project alignment and scope definition.
TSK-002 | Requirements Gathering | Sarah Johnson | 2024-04-02 | 2024-04-10 | 9 | In Progress | High | TSK-001 | Collect stakeholder needs and document functional requirements.
TSK-003 | Design Phase | Mike Brown | 2024-04-11 | 2024-04-25 | 15 | Planned | Medium | TSK-002 | Create wireframes and UI mockups for the application.
TSK-004 | Development Phase | Lisa Chen | 2024-04-26 | 2024-05-30 | 35 | Not Started | High | TSK-003 | Implement core features based on approved design.
TSK-005 | Testing & QA | David Lee | 2024-06-01 | 2024-06-15 | 15 | Planned | High | TSK-004 | Conduct unit, integration, and user acceptance testing.
TSK-006 | Deployment | Anna White | 2024-06-16 | 2024-06-18 | 3 | Not Started | High | TSK-005 | Release application to production environment.