## Worksheet
Date | Task | Assignee | Start Time | End Time | Status | Duration (hrs) | Notes
2024-04-01 | Project Kickoff Meeting | John Doe | 09:00 | 10:30 | Completed | 1.5 | All stakeholders present; goals defined.
2024-04-02 | Requirements Gathering | Sarah Lee | 10:00 | 13:00 | In Progress | 3 | Client feedback collected; draft document under review.
2024-04-03 | Design Review | Mike Chen | 14:00 | 16:30 | Pending | 2.5 | Final design to be approved by client.
2024-04-04 | Development Start | David Kim | 09:00 | 17:30 | Not Started | 8.5 | Frontend and backend setup initiated.