## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Progress (%)
T001 | Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-03 | 3 | On Track | High | None | 100%
T002 | Requirements Gathering | Mike Chen | 2024-04-04 | 2024-04-15 | 12 | In Progress | High | T001 | 65%
T003 | Design Phase | Lisa Wong | 2024-04-16 | 2024-05-05 | 20 | Planned | Medium | T002 | 0%
T004 | Development Phase | David Park | 2024-05-06 | 2024-06-30 | 65 | Not Started | High | T003 | 0%
T005 | Testing & QA | Emma Reed | 2024-07-01 | 2024-07-31 | 30 | Planned | High | T004 | 0%
T006 | Project Closure | Sarah Johnson | 2024-08-01 | 2024-08-05 | 5 | Not Started | Low | T005 | 0%