## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation
T-001 | Project Initiation & Planning | John Doe | 2024-03-01 | 2024-03-15 | 15 | High | Planned |  | Project Manager, Stakeholder Team
T-002 | Requirements Gathering | Jane Smith | 2024-03-16 | 2024-04-05 | 21 | High | In Progress | T-001 | Business Analysts, Stakeholders
T-003 | System Design Phase | Mike Johnson | 2024-04-06 | 2024-05-10 | 35 | Medium | Planned | T-002 | Design Team, IT Lead
T-004 | Development & Coding | Sarah Lee | 2024-05-11 | 2024-07-15 | 65 | High | Not Started | T-003 | Software Developers, QA Lead
T-005 | Testing & Quality Assurance | David Kim | 2024-07-16 | 2024-08-10 | 35 | High | Not Started | T-004 | QA Team, Test Engineers
T-006 | Deployment & Go-Live | Lisa Wong | 2024-08-11 | 2024-08-15 | 5 | Critical | Not Started | T-005 | DevOps Team, Operations Manager