## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation | Milestone? | Notes
T-001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | High | Completed | - | Team Lead, Project Manager | Yes | Set up project goals and team roles.
T-002 | Requirements Gathering | Sarah Lee | 2024-04-02 | 2024-04-15 | 14 | High | In Progress | T-001 | Business Analyst, UX Lead | No | Collect user needs and define functional requirements.
T-003 | System Design Phase | Michael Chen | 2024-04-16 | 2024-05-05 | 21 | Medium | Not Started | T-002 | Architect, Dev Team | Yes | Finalize wireframes and technical architecture.
T-004 | Development Phase | Team A | 2024-05-06 | 2024-07-15 | 71 | High | Not Started | T-003 | Full Dev Team, 5 Engineers | No | Build core modules and integrate APIs.
T-005 | Testing & Quality Assurance | Lisa Park | 2024-07-16 | 2024-08-10 | 25 | High | Not Started | T-004 | QA Team, Automation Tools | Yes | Conduct unit, integration, and UAT testing.
T-006 | Deployment to Production | David Kim | 2024-08-11 | 2024-08-13 | 3 | High | Not Started | T-005 | Ops Team, Cloud Admin | Yes | Deploy and monitor live environment.
T-007 | Post-Deployment Review | John Smith | 2024-08-14 | 2024-08-15 | 2 | Medium | Not Started | T-006 | Project Manager, Dev Team | Yes | Evaluate performance and gather feedback.