## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Duration (Days) | Dependencies | Progress (%)
T001 | Project Initiation | Sarah Johnson | 2024-04-01 | 2024-04-10 | In Progress | High | 10 | None | 60%
T002 | Requirements Gathering | Michael Chen | 2024-04-11 | 2024-04-25 | Not Started | High | 15 | T001 | 0%
T003 | Design Phase | Emily Davis | 2024-04-26 | 2024-05-10 | In Progress | Medium | 15 | T002 | 40%
T004 | Development Phase | James Wilson | 2024-05-11 | 2024-06-15 | Not Started | High | 45 | T003 | 0%
T005 | Testing & QA | Linda Park | 2024-06-16 | 2024-07-05 | Not Started | High | 20 | T004 | 0%
T006 | Deployment | David Brown | 2024-07-06 | 2024-07-10 | Not Started | Medium | 5 | T005 | 0%