## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Budget Allocation ($) | Status | Progress (%) | Priority
T001 | Project Initiation & Feasibility Study | 2024-03-15 | 2024-03-25 | 10 | Sarah Johnson | 15,000.00 | Completed | 100% | High
T002 | Market Analysis & Competitive Review2024-03-26 | 2024-04-10 | 15 | Michael Chen | 25,000.00 | In Progress | 75% | High
T003 | Product Requirements Definition | 2024-04-11 | 2024-05-15 | 35 | Linda Patel | 30,000.00 | Not Started | 0% | Critical
T004 | Design & UI Prototyping | 2024-05-16 | 2024-06-30 | 45 | David Kim | 40,000.00 | Planned | 20% | Medium
T005 | Development & Integration Phase | 2024-07-01 | 2024-11-30 | 150 | Team A - Dev Leads | 200,000.00 | Not Started | 0% | Critical