## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed |  | Finalize team roles and project scope.
T002 | Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | 14 | High | In Progress | T001 | Interview stakeholders and document needs.
T003 | UI/UX Design Phase | Sarah Lee | 2024-04-16 | 2024-05-10 | 25 | Medium | Not Started | T002 | Design wireframes and user flows.
T004 | Development Phase (Frontend) | Mike Chen | 2024-05-11 | 2024-06-30 | 60 | High | Not Started | T003 | Implement responsive design.
T005 | Development Phase (Backend) | Lena Torres | 2024-05-11 | 2024-07-15 | 65 | High | Not Started | T004 | Set up API endpoints and database.
T006 | Testing & QA | David Kim | 2024-07-16 | 2024-08-15 | 30 | High | Not Started | T004, T005 | Conduct functional and usability tests.
T007 | Deployment & Go-Live | Emily Wong | 2024-08-16 | 2024-08-16 | 1 | High | Not Started | T006 | Launch the application to production.
T008 | Post-Launch Support | Team Lead | 2024-08-17 | 2024-10-31 | 75 | Low | Not Started |  | Monitor performance and resolve issues.