## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Responsible Person | Priority | Status
T001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Alice Johnson | High | In Progress
T002 | Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | Bob Smith | Medium | Not Started
T003 | Design Phase | 2024-03-16 | 2024-03-25 | 10 | Carol Davis | High | Planned
T004 | Development Phase | 2024-03-26 | 2024-04-15 | 20 | David Lee | Critical | Not Started
T005 | Testing & Quality Check | 2024-04-16 | 2024-04-30 | 15 | Eva Martinez | High | Scheduled
T006 | Deployment & Training | 2024-05-01 | 2024-05-10 | 10 | Frank White | Medium | Not Started