## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Responsible Team
T-001 | Project Kickoff Meeting | Jane Doe | 2024-03-15 | 2024-03-15 | 1 | Completed | High | None | Project Management Team
T-002 | Requirements Gathering | John Smith | 2024-03-16 | 2024-03-25 | 10 | In Progress | High | T-001 | Business Analysis Team
T-003 | Design Phase Final Review | Lisa Wong | 2024-04-01 | 2024-04-05 | 5 | Planned | Medium | T-002 | UX & Design Team
T-004 | Development Phase Start | Mike Taylor | 2024-04-10 | 2024-05-31 | 63 | Not Started | High | T-003 | Engineering Team
T-005 | Testing & QA Validation | Sarah Kim | 2024-06-15 | 2024-07-15 | 30 | Not Started | High | T-004 | QA Team