## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Notes
T-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | High | None
T-002 | Requirements Gathering | John Smith | 2024-04-02 | 2024-04-10 | 9 | In Progress | High | T-001 | Finalize user stories and scope.
T-003 | Design Phase | Alex Chen | 2024-04-11 | 2024-04-25 | 15 | Planned | Medium | T-002 | Wireframes and UI mockups.
T-004 | Development Phase | Sam Lee | 2024-04-26 | 2024-05-31 | 36 | Not Started | High | T-003 | Backend and frontend implementation.
T-005 | Testing & QA | Linda Park | 2024-06-01 | 2024-06-15 | 15 | Not Started | High | T-004 | Unit, integration, and user acceptance testing.
T-006 | Deployment | Mike Johnson | 2024-06-16 | 2024-06-16 | 1 | Not Started | High | T-005 | Go live on production server.