## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
T-001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | Completed | High | None
T-002 | Requirements Gathering | Anna Lee | 2024-04-02 | 2024-04-15 | 14 | In Progress | High | T-001
T-003 | Design Phase Finalization | Michael Chen | 2024-04-16 | 2024-04-30 | 15 | Not Started | Medium | T-002
T-004 | Development Begins | Sarah Kim | 2024-05-01 | 2024-05-31 | 31 | Not Started | High | T-003
T-005 | Testing & QA Review | David Ross | 2024-06-01 | 2024-06-15 | 15 | Not Started | High | T-004
T-006 | Deployment & Go-Live | Lisa Wong | 2024-06-16 | 2024-06-30 | 15 | Not Started | Critical | T-005