## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (days) | Priority | Status | Dependencies | Progress (%)
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | 1
TSK-002 | Requirement Gathering | John Doe | 2024-04-02 | 2024-04-15
TSK-003 | Design Phase Initiation | Lisa Chen | 2024-04-16 | 2024-05-10
TSK-004 | Development Setup | Mike Taylor | 2024-05-11 | 2024-05-25
TSK-005 | Core Module Development | Sarah Kim | 2024-05-26 | 2024-07-15
TSK-006 | Testing & QA Phase | David Wong | 2024-07-16 | 2024-08-31
TSK-007 | Deployment Planning | Emma Reed | 2024-09-01 | 2024-09-15
TSK-008 | Final Review & Sign-off | All Team Members | 2024-09-16 | 2024-09-16
Total Tasks: |  |  |  |  | 8