## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T-001 | Project Initiation | John Smith | 2024-03-01 | 2024-03-05 | 5 | High | In Progress |  | Finalize project scope and charter.
T-002 | Requirements GatheringSarah Lee | 2024-03-06 | 2024-03-15 | 10 | High | Planned | T-001 | Collect stakeholder needs and define requirements.
T-003 | Design Phase | Michael Brown | 2024-03-16 | 2024-03-25 | 10 | Medium | Not Started | T-002 | Develop wireframes and system architecture.
T-004 | Development Phase | Lisa Chen | 2024-03-26 | 2024-04-15 | 21 | High | Not Started | T-003 | Build core functionality according to design.
T-005 | Testing Phase | David Park | 2024-04-16 | 2024-04-30 | 15 | High | Not Started | T-004 | Conduct unit, integration, and user testing.
T-006 | Deployment & Handover | Anna Garcia | 2024-05-01 | 2024-05-03 | 3 | Medium | Not Started | T-005 | Deploy to production and train users.