## Project Plan - Task Scheduling
Project Plan – Task Scheduling (One Page Template)
Task ID | Task Description | Owner | Start Date | End Date | Status | Priority th> | Durations (Days) th>
T-001 | Project Initiation & Planning | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | High | 15
T-002 | Requirement Gathering & AnalysisMark Johnson | 2024-04-16 | 2024-05-10 | Pending Approval | 35
T-003 | Design Phase – UI/UX DevelopmentLisa Chen | 2024-05-11 | 2024-06-15 | Done
T-004 | Development & Integration TestingAlex Rivera | 2024-06-16 | 2024-08-31 | Pending Review
T-005 | Deployment to Production EnvironmentSophia Kim | 2024-09-01 | 2024-09-15 | Not Started
T-006 | User Training & DocumentationTom Wilson | 2024-09-16 | 2024-10-15 | Planned
T-007 | Post-Launch Evaluation & Feedback ReviewJane Smith | 2024-10-16 | 2024-11-30 | Not Started