## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (days) | Priority | Status | Dependencies
T-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | None
T-002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | T-001
T-003 | UI/UX Design | Alex Chen | 2024-04-11 | 2024-04-25 | 15 | Medium | Planned | T-002
T-004 | Backend Development | Mike Brown | 2024-04-26 | 2024-05-15 | 20 | High | Not Started | T-003
T-005 | Frontend Development | Sarah Lee | 2024-05-16 | 2024-05-31 | 16 | Medium | Not Started | T-004
T-006 | Testing & QA | Chris Taylor | 2024-06-01 | 2024-06-15 | 15 | High | Not Started | T-005
T-007 | Go Live & Training | Lisa Wong | 2024-06-16 | 2024-06-30 | 15 | Medium | Not Started | T-006