## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (days) | Priority | Status | Dependencies | Resources
T-001 | Project Initiation | John Doe | 2024-03-01 | 2024-03-05 | 5 | High | In Progress | None | Project Manager, Finance Lead
T-002 | Requirements Gathering | Jane Smith | 2024-03-06 | 2024-03-15 | 10 | High | Not Started | T-001 | Business Analysts, Stakeholders
T-003 | Design Phase | Mike Johnson | 2024-03-16 | 2024-03-25 | 10 | Medium | Not Started | T-002 | UI/UX Design Team
T-004 | Development Phase | Sarah Lee | 2024-03-26 | 2024-04-15 | 20 | High | Not Started | T-003 | Software Engineers, QA Team
T-005 | Testing & QA | David Brown | 2024-04-16 | 2024-04-30 | 15 | High | Not Started | T-004 | QA Team, Testers
T-006 | Deployment & Go-Live | Lisa Chen | 2024-05-01 | 2024-05-03 | 3 | Medium | Not Started | T-005 | DevOps Team, Operations